## Task Sheet
Task | Responsibility | Timeline | Budget | Dinner Needs | Budget | Decor Needs | Budget
Make Nomination Form Public | SSS Steer Chair | 2-3 months prior |  | Meat (Chicken or Steak) |  | Table Cloths
Inductee Selections | Nomination Committee | 1 month prior |  | Potatoes |  | Flowers
Regret Letters to Nominators | SSS Steer Chair | 1 month prior |  | Green Beans |  | Lights
Contact Inductees to Inform Selection | Nomination Committee | 1 month prior |  | Rolls
Confirm Guest Speaker | Nomination Committee | 1 month prior |  | Cake (2)
Confirm Musical Support | SSS Steer Chair | 1 month prior |  | Brownies |  | Nomination Form Needs
Send Invitations (Inductees) | SSS Admin | 1 month prior |  | Iced Tea (Sweet/Unsweet) |  | Nominee Address
Send Invitations (Honored Guests) | SSS Admin | 1 month prior |  | Water |  | Nominee Phone #
Media Announcement | SSS Media Coordinator | 1 month prior |  | Plates |  | Nominee Email Address
Organize Attendee Spreadsheet | SSS Steer Chair | 1 month prior |  | Silverware
Update HOF Case | SSS Art Dept | 3 weeks prior |  | Napkins
Gather Pics and Bios from Inductees | SSS Steer Chair | 3 weeks prior |  | Cups
Order Plaques (Inductees) | SSS Steer Chair | 3 weeks prior |  | Butter
Print and Frame Heart of Sparta | SSS Steer Chair | 2 weeks prior |  | Salt/Pepper
Finalize Program | SSS CTE | 2 weeks prior |  | 6 warmers (2 each item)
Organize Student Serving/Clean Crew | SSS Steer Chair | 2 weeks prior |  | Take Home Boxes
Chair Covers Process | SSS OCS Dept | 1-2 weeks prior |  | Serving Spoons/Tongs
Create Video to Play | SSS Steer Chair | 1 week prior
Purchase Dinner Items | SSS Steer Chair | 1 week prior
Purchase Decor Items | SSS Steer Chair | 1 week prior
Order Corsages | SSS Steer Chair | 1 week prior
Final Guest List Review | All Committees | 3-5 days prior
Share Bios with Guest Reader | SSS Steer Chair | 3-5 days prior
Roll Silverware Sets | SSS OCS Dept | 3-5 days prior
Cafeteria Organization/Setup | SSS Steer Chair | 1 day prior
Reserved Table Tents | SSS Admin | 1 day prior
Begin Cooking for Dinner | SSS Steer Chair | 5 hours prior (warm)
Media Setup | SSS Admin | 1 hour prior
Money Box with Change ($10, $5) | SSS Admin | 1 hour prior
Photographer | SSS Admin | during
Student Serving and Clean Up Crew | SSS Steer Chair | during

## People to Invite
Role of Honored Guests | Invitations to be Paid
Superintendent JCPS | Chamber of Commerce
Area Superintendents JCPS | SSS Staff (discounted price?)
Board of Education
Cabinet Members
State Representatives